CENTRAL POWER & TELECOM SERVICES

302 TRADESMENS PARK DR. #100

HUTTO, TEXAS 78634

METHOD OF PROCEDURE

VERIZON WIRELESS

Mod Project

- SITE INFO AND SCHEDULE

|  | SITE NAME; FUZE ID; PS LOC #; SITE #; DATE. JERRY_BOYLES_RD; 17520291; 5000249629; 616636943; 10/12/26 8:00 PM to 10/16/26 8:00 AM. |  |
| --- | --- | --- |

- JOB DESCRIPTION

- Carr Add

- EQUIPMENT

Macro Mod

- PERSONNEL

- SHANE ROBERTS (LEAD-PROJECT MANAGER) 512-937-0609

- TYLER RAY (DAY LEAD) 940-372-4814

- SITE SAFETY

ALL EMPLOYEES WILL BE INSTRUCTED TO THEIR SPECIFIC TASKS PRIOR TO INSURE SAFE PRACTICES IN THEIR DEDICATED TASKS.  PROPER PPE TO EACH TASK WILL BE IMPLEMENTED.

ie

SAFETY GLASSED WHEN DRILLING

HARD HATS WHEN OVERHEAD WORK IS BEING PERFORMED

MASK WHEN EXPOSED TO INHALATION RISKS

PROTECTIVE GLOVES WHEN HANDLING EQUIPMENT AND BATTERIES

- DETAILED STEP-BY-STEP PROCEDURE

LEAD PERSONNEL WILL CONTACT OPS 24HRS PRIOR TO PROJECT

CREW WILL ARRIVE AT LEAST AN HOUR BEFORE SITE IS SCHEDULED TO BE SHUT DOWN FOR PROJECT

UPON ARRIVAL LEAD TECH WILL LOG INTO IVR

LEAD TECHS WILL BEGIN INSPECTING EXISTING EQUIPMENT FOR ANY PRIOR ISSUES

LEAD TECHS WILL SURVEY THAT THE NEW UPGRADED EQUIPMENT WILL NOT HAVE ANY CLEARANCE ISSUES WITH EXISTING SITE CONDITIONS AND/OR EQUIPMENT

ONCE LEAD TECHS HAVE DETERMINED TO MOVE FORWARD WITH THE PROJECT HELPER(s) WILL BEGIN UNLOADING ANY TOOLS AND/OR EQUIPMENT AS WELL AS ANY MATERIAL NEEDED TO PERFORM PROJECT. THEY WILL ENSURE NOTHING IS MISSING THAT ENABLE THE CREW TO PERFORM THE PROJECT.

LEAD TECH WILL TAKE PHOTOS OF EXISTING EQUIPMENT

LEAD TECH WILL VERIFY ALL CONTRACTORS INVOLVED WITH THE PROJECT ARE PRESENT AND READY

HELPERS WILL BEGIN PREP ON THE NEW EQUIPMENT TO BE INSTALLED

LEAD TECH WILL CONTACT NOCC OR CONFER WITH VZW TECH ON SITE AT TIME OF SHUT DOWN SCHEDULE TO VERIFY ANY OUTSTANDING ISSUES BEFORE PROJECT IS STARTED.

**For a HUB or Microwave site, technicians will wire a temporary plant up and transfer the Loads needed to keep up the associated sites, so that other sites are not affected**

ANY BATTERIES AT THIS TIME THAT NEED TO BE REMOVED WILL ALSO BE DISCONNECTED AND REMOVE IF APPLICABLE

RELOCATION OF ANY EXISTING EQUIPMENT WILL BEGIN

ALL NECESSARY CONNECTIONS WILL BE MADE

LEAD TECH WILL TERIMINATE D/C POWER FROM ALL EQUIPMENT

HELPERS WILL LABEL ALL CONNECTIONS

HELPERS WILL BEGIN CLEANING WORK AREA

LEAD TECH WILL VERIFY ALL CONNECTIONS

CHECK FOR CORRECT VOLTAGE FROM BATTERIES

TERMINATE NEW ALARM CABLE

BEGIN THE START-UP OF ALL EQUIMENT.

ONCE EQUIPMENT IS RUNNING WITH NO ISSUES THE VZW TECH WILL BEGIN BRINGING THE SITE BACK ON AIR.

NO ISSUES CONFIRMED HELPERS WILL BEGIN CLEAN-UP

PICTURES WILL BE TAKEN OF FINISHED PROJECT

IF OUR CREW IS THE LAST TO LEAVE SITE, WE WILL SECURE THE ENTIRE SITE

LOG OUT OF IVR

TURN IN POST ACTIVITY WORKSHEET

- TESTS AND RESULTS

BATTERY VOLTAGE WILL BE TESTED PRIOR TO START UP

PLANT VOLTAGE WILL BE TESTED PRIOR TO BTS POWER UP

- EMERGENCY RESTORATION PLAN

IN THE EVENT OF NEW EQUIPMENT FAILURE OR ANY PROBLEMS THAT MAY CAUSE US TO EXCEED TIME CONSTRAINTS. WE WILL WORK WITH THE VZW TECH TO RESOLVE ANY ISSUES AND SURVEY OUR OPTIONS. WORSE CASE SENARIO, OLD EQUIPMENT WILL BE RE-INSTALLED IN MOST CASES THIS WILL NOT BE AN OPTION !!!

- ADDITIONAL INFO AND COMMENTS

SCHEDULED WINDOW: 10/12/26 8:00 PM TO 10/16/26 8:00 AM

LEAD INSTALLER: TYLER RAY - 940-372-4814 - tyler@driventelecom.com

SCOPE OF WORK:

GROUND: Site needs Ciena 5164 and Westell needs to be installed and migrated. CDU30 to uAPDF Conversion. Move CDU30 down.  Install SPR vDU and FSU, Load IP details, test server validation, complete GPS DTF.  Decom CDU30 after conversion.  Install Blank plates to direct the AC airflow to the equipment. Swap GEN 1 CommScope PS to RayCap PS. Decom Cisco router after confirming site is migrated. Ensure all equipment is plugged into Westell per VZ Standards.Relocate indoor OVP to outdoor OVP.